## Sheet1
S# | Description | Project Type | Status | Customer Contact | ETA | Shepardti | Proposal Submitted
1 | Price Grab - Competetive Prioce scraping from Portals | Agentic Automation | UAT | Ganesh | 2022-08-01 | Dr.Venkat | Yes
2 | RAG - Learning Agent | RAG DB | UAT | Ajay / Kushal | 2018-08-01 | Dr.Venkat | POC
3 | GA dashboards | Dashboards | Ongoing | Srishti / Uma | 45852 | Sakthi / Denesh | Yes
4 | Auto Scheduling of reports emails | Dashboards | Completed | Srishti / Uma | 45847 | Denesh | Yes
5 | DataWare house | DWH | Proposal Submitted | Srishti / Uma | NA | Dr Venkat | Yes
6 | Transaction DB integration for BOM and BOB | Automation | On-hold | Srishti / Uma | NA | Sakthi / Denesh | No
7 | Syncing of Looker Studio Fynd - HDFC and existing Dashboards | Automation | Yet to start | Uma / Nishit Bhagya | NA |  | No
8 | Customer search page | Dashboard | On-hold | Nishit Gandhi | NA | Thawpeek / DC | No
9 | FAQ - ChatBOT - Customer Support | RAG DB | work-In-Progress | Nishit Gandhi | 45883 | Dr.Venkat | Yes
10 | SFDC - CRM tracking and syncing | Automation | On-hold | Nishit Gandhi |  | Thawpeek | No
11 | Sales & Margin Report | Automation | UAT | Manju Cristopher | 45879 | Thawpeek | Yes
12 | Payment Schedule | Automation | UAT | Manju Cristopher | 45853 | Thawpeek | PoC
13 | Order reconciliation | Automation | UAT | Manju Cristopher | 45853 | Thawpeek | Yes
14 | Margin Decision Report | Automation | UAT | Manju Cristopher | 45853 | Thawpeek | Yes
15 | HR-Recuitment Automation | Agentic Automation | Yet to start |  | NA |  | PoC