## Price Grab
Description | Value
Heading | Price Grab
Purpose | The software aggregates and compares prices from Amazon, Flipkart, Croma, and Reliance to optimize pricing strategies for enhanced marketability.
Actionable Data | Provides real-time price comparisons, competitor pricing trends, and demand fluctuations to inform dynamic pricing decisions.
Go-Live Date | UAT in progress and scheduled to go-live by Aug-20.
Contact Points | CC - Nishant Bhagaya / Ganesh; ST - Dr Venkat
Challenges / Remarks | Overcomes Amazon's bot detection algorithms using IP rotation and CAPTCHA-solving techniques to discreetly scrape prices. Outstanding Items - Input files awaited from CC(Ganesh) for remaining portals.
Status | Proposal submitted and pending approval.
Details | 4 Portals to be incorporated under price Grab Amazon - Deployed - Live Flipkart - Under Internal testing Croma / Reliance - Awaiting Input files from CC
Date Updated(dd/mm/yyyy) | 2025-06-08
Progress | 90%
Mode | UAT

## RAG
Description | Value
Heading | Retrieval Aumented Service (RAG)
Purpose | The RAG-Service enables users to upload PDF, Word, text, Excel, or PowerPoint documents and query their content for enhanced information retrieval and analysis. Intent is to create a virtual agents / service which can be leveraged to support activities like learning, customer support etc to boost employee productivity
Actionable Data | Provides accurate, context-aware responses to user queries based on document content, facilitating informed decision-making.
Go-Live Date | Tentative go live planned for end of August
Contact Points | CC - Kushal, CX - Nishit; ST - Dr Venkat
Challenges / Remarks | Achieves accuracies above 95%, with additional testing required to ensure reliability.
Status | POC - UAT in progress. ETA - 21st Aug
Details | Two projects under RAG Service 1. RAG Service - POC UAT in progress 2. RAG Service CX - Deployed for POC - UAT, Final scoping under review for CX Support BOT
Date Updated(dd/mm/yyyy) | 2025-06-08
Progress | 80%
Mode | UAT

## GA Insights
Description | Value
Heading | GA dashboards
Purpose | The GA dashboards enables users to visualise the different metrics using the GA4 data and transactional data from databases such as MySql and Postgres.
Actionable Data | The dashboard gives an insight into user behaviour, customer segmentation, volume based metrics to track sales and margin across various categories, products.
Go-Live Date | 1. IDFC-Tripstacc - 18/Jun/25 2. IDFC Shopstacc - Tentative Go Live - 18th Aug 3. Scheduled Reports - 18/Jun/25 Other Dashboards - Under internal Review (BOB,ET,BOM) - Tentative End of Aug HDFC - KPI's scoping in progress - ETA under discussion
Contact Points | CC - Srishti / Uma ; ST - Sakthi / Abhinav
Challenges / Remarks | Dashboard - HDFC - KPI's scoping in progress with CC team. Fynd and Payment reports still under finalization with CC Transction DB for other staccs - Replication cost and approval still under discussion internally by CC team Improvements Done - Bigquery Support added to improve performance of Dashboards to overcome postrgres technical syncing issues Potential Risks - Website updates will lead to data mapping issues causing incorrect data to be reflected in Dashboards. Potential issue with UI changes impacting GA
Status | Live Dashboards - 1 (Tripstacc) Ready for Go Live - 1 (Shopstacc) Under Internal Review - 2 (ET, BOM) In UAT - 1 (BOB) Requirement Scoping - 1 (HDFC) Email Scheduler - Live
Details | Current Status - 5 Dashboards 1. IDFC-Tripstacc- 18 Filters, 67 KPIs 2. IDFC-Shopstacc- 17 filters, 56 KPIs 3. BOB card- 8 filters, 39 KPIs 4. BOM- 8 filters, 36 KPIs- Internal review in progress 5. ET- 8 filters, 26 KPIs- Internal review in progress HDFC - Intial configuration for GA metrics in progress Performance KPI's being finalized by CC team Transaction DB syncing - On-hold - Awaiting updates from CC on replication
Date Updated(dd/mm/yyyy) | 2025-06-08
Progress | 90%
Mode | Implemented

## Finance Automation
Description | Value
Heading | Finance Automation
Purpose | Automate the calculations being done for HDFC using manual excel macros to maintain vendor cost master, MOP and selling margins to assist in sales and margin reporting and revenue tracking (sales/refunds)
Actionable Data | Implement automation to capture the various input sources like FYND report, Payment Gateway report, Vendor cost master, Mark up master and provide auto calculations for various reports
Go-Live Date | Tentative ETA - 22-08-2025
Contact Points | CC - Manju, Nishant, Ganesh ; ST - Thawpeek / Abhinav
Challenges / Remarks | 1. Input report layouts still being finalized for FYND and Payment gateway 2. Input test data for Payables automation still pending with CC team 3. Change requests coming in on ad-hoc basis as the system is being tested in UAT
Details | Reports - 1. Integration of FYND, PAYU and Vendor Cost Master completed 2. MOP master import setup completed - UAT in progress 3. 4 reports delivered for UAT on 15th July CR received for Filters to be provided on reports and develop export intgerations with Power BI and Looker Studio
Status | UAT delivery - 18/Jul/25
Date Updated(dd/mm/yyyy) | 2025-06-08
Progress | 95%
Mode | UAT

## Datawarehouse
Description | Value
Heading | Datawarehouse
Purpose | Streamline and consolidate multiple segments and sources of sales and input data for understanding and deriving better sales insights to grow and run business better
Actionable Data | Setup of pipelines to ingest data from various sources and setup ETL processes to transform the data into a more insight driven format. To assist business to drive more revenue growth
Go-Live Date | Awaiting timelines from CC team
Contact Points | CC - Ayesha/Srishti/Uma ; ST - Dr Venkat
Challenges / Remarks | No Updates received from CC post submission of proposal
Status | Proposal submitted on 09/Jun/25 Still under review with CC team till date
Date Updated(dd/mm/yyyy) | 2025-06-08
Progress | 20%
Mode | Development

## HR Automation
Description | Value
Heading | HR Automation
Purpose | Provide Agentic support for L1 screening and parsing of resume to help shortlist interview candidates for recruitment
Actionable Data | Agent to provide facility to generate Job Descriptions for various roles and implement a mathematical model to calculate the profile fitment score against the job posting
Go-Live Date | POC instance setup in progress ETA - 15th Aug
Contact Points | CC - Kunal/Sourabh Kala ; ST - Dr Venkat
Challenges / Remarks
Status | Procurement of requisite infra in progress
Date Updated(dd/mm/yyyy) | 2025-06-08
Progress | 30%
Mode | Development

## CX Agentic Framework
Description | Value
Heading | CX Agentic Framework
Purpose | Boost productivity for CX Agents on ground by having customer CRM data accessible easily and faster
Actionable Data | Provide an integrated UI to the CX Agent on ground to simplify the way to identify the originating customer and retrieve their respective transactional data without searching across multiple portals
Go-Live Date | Last week of Augus 2025
Contact Points | CC - Nishit Gandhi ; ST - Deva / Abhinav
Challenges / Remarks | Possible Challenges - 1. Would require replication of existing transaction DB's which will incur cost for CC 2. If DB approach is ruled out then screen scrapping would not be appropriate for accuracy of data capture 3. Data Security perspective to be reviewed with CC team (Rajeev / Kunal) if agent ID's could be created to export reports on a scheduled basis
Status | Initial risk and requirement scoping in progress
Details | Initial calls with Rajeev and team to be setup for next week
Date Updated(dd/mm/yyyy) | 2025-06-08
Progress | 20%
Mode | Development

## Integration - Agentic Framework
Description | Value
Heading | Intgeration - Agentic Framework
Purpose | Sync ticket information across bank SFDC platform and V-Tiger CRM
Actionable Data | Provide a way for the CX agent to reconcile and monitor the daily ticket and update summary with bank
Go-Live Date | Initial automation feasibility in progress
Contact Points | CC - Nishit Gandhi ; ST - Thawpeek / Abhinav
Challenges / Remarks | Risk - SFDC restricts agents to scrape data from screen due to unaidentifiable tags. Ticket classification being done by bank and in V-tiger is different and may need NLP for category corelation
Status | Proposal to be submitted post initial feasibility check
Details | feasibility under progress
Date Updated(dd/mm/yyyy) | 2025-06-08
Progress | 10%
Mode | Development